## INSTRUCTIONS
INSTRUCTIONS
The following document is used to record and track access requests across the execution of a customer implementation.
The Access Tracker tab is used to track all pending requests, with each row corresponding to a single access request. The values in the columns can be selected from the dropdown shown.
The List tab is used to create the dropdown options under each column in the Access Tracker tab. These can be customized as needed, and the tab can be hidden when sharing externally.
This document can be maintained internally and/or sent to client stakeholders as part of tracking and driving appropriate accesses during implementation.
GUIDE FOR FILLING THE LIST TAB
Process Name - Populate with the unique names of the processes for which PDDs are prepared in an engagement.
User Name - Update the names of the persons who will need access. For unattended bots, initiate the row with 'robot01' and update the robot's service account after it is known.
Application - Update with the names of the applications to which access will be required.
Requested By - Populate with the names of the individuals who would have asked for an item to be tracked in this workbook.
Assigned To - Populate with the names of the client's accountable for seeing the request through completion.
Provisioning System - Update the different ways for access to end point to be requested.

## Access Tracker
Vendor Onboarding- Application Access Tracker
| User details |  |  |  | Application details |  |  |  | Request details |  |  |  | Provisioning details
| Process Name | User Name | Account Type | Purpose | Application | Endpoint/Location | Environment | Access Level | Requested By | Assigned To | Requested Date | Request ID | Provisioning System | Provisioned Date | Access Confirmation Date | Access End Date | Status | Comments
| Vendor Onboarding | ABC | User | Develop | ACME System 1 |  | Lower | Read-write | qrs | abc | 2023-05-06 |  | Client's Infosec Syst-x |  |  |  | Confirmed
| Vendor Onboarding | ABC | User | Develop | ACME System 3 |  | Lower | Read-only | bcd | xyz | 2023-05-06 |  | Client's Infosec Syst-x |  |  |  | Requested
| Vendor Onboarding | ABC | User | Develop | Outlook |  | Lower | Read-write | bcd | xyz | 2023-05-06 |  | ServiceNow |  |  |  | Requested
| Vendor Onboarding | UATRobot | Robot | Test | ACME System 1 |  | Lower | Read-write | qrs | abc | 2023-05-06 |  | Client's Infosec Syst-x |  |  |  | Requested
| Vendor Onboarding | UATRobot | Robot | Test | ACME System 3 |  | Lower | Read-only | qrs | abc | 2023-05-06 |  | Client's Infosec Syst-x |  |  |  | Requested
| Vendor Onboarding | UATRobot | Robot | Test | Outlook |  | Lower | Read-write | bcd | xyz | 2023-05-06 |  | ServiceNow |  |  |  | Requested
| Vendor Onboarding | ProdRobot | Robot | Production | ACME System 1 |  | Prod | Read-write | bcd | xyz | 2023-05-06 |  | Client's Infosec Syst-x |  |  |  | Requested
| Vendor Onboarding | ProdRobot | Robot | Production | ACME System 3 |  | Prod | Read-only | bcd | xyz | 2023-05-06 |  | Client's Infosec Syst-x |  |  |  | Requested
| Vendor Onboarding | ProdRobot | Robot | Production | Outlook |  | Prod | Read-write | bcd | xyz | 2023-05-06 |  | ServiceNow |  |  |  | Requested

## List
Process Name | User Name | Account Type | Purpose | Application | Endpoint/Location | Environment | Access Level | Requested By | Assigned To | Requested Date | Request ID | Provisioning System | Provisioned Date | Confirmation Date | Access End Date | Comments
Vendor Onboarding | ABC | User | Develop | ACME System 1 |  | Lower | Read-only | bcd | abc | Not requested |  | ServiceNow
| UATRobot | Robot | Test | Outlook |  | Prod | Read-write | qrs | xyz | Requested |  | Client's Infosec Syst-x
| ProdRobot | Exchange / SMTP server | Production | ACME System 3
|  | Service Account RDP Access | Install
AD Group account for Support