## Complexity Calculator
| Process Complexity Calculator |  | Automation Use Case #1 |  |  |  | Automation Use Case #2 |  |  |  | Automation Use Case #3 |  |  |  | Automation Use Case #4 |  |  |  | Automation Use Case #5 |  |  |  | Automation Use Case #6 |  |  |  | Automation Use Case #7
|  |  | Vendor Onboarding |  |  |  | <Use Case #2 Name> MAXED |  |  |  | <Use Case #3 Name> |  |  |  | <Use Case #4 Name> |  |  |  | <Use Case #5 Name> |  |  |  | <Use Case #6 Name> |  |  |  | <Use Case #7 Name>
|  |  | Complexity Score | 24 |  |  | Complexity Score | 0 |  |  | Complexity Score | 0 |  |  | Complexity Score | 0 |  |  | Complexity Score | 0 |  |  | Complexity Score | 0 |  |  | Complexity Score | 0
| *Please update only Answer to get the score and complexity. |  | Calculated Complexity Level | Medium |  |  | Complexity Level | Fill out all answers |  |  | Complexity Level | Fill out all answers |  |  | Complexity Level | Fill out all answers |  |  | Complexity Level | Fill out all answers |  |  | Complexity Level | Fill out all answers |  |  | Complexity Level | Fill out all answers
|  |  | Warnings? | No |  |  | Warnings? | No |  |  | Warnings? | No |  |  | Warnings? | No |  |  | Warnings? | No |  |  | Warnings? | No |  |  | Warnings? | No
|  |  | Tech Lead Assessment of Complexity |  |  |  | Tech Lead Assessment of Complexity |  |  |  | Tech Lead Assessment of Complexity |  |  |  | Tech Lead Assessment of Complexity |  |  |  | Tech Lead Assessment of Complexity |  |  |  | Tech Lead Assessment of Complexity |  |  |  | Tech Lead Assessment of Complexity
|  |  | # of Warnings | 0 |  |  | # of Warnings | 0 |  |  | # of Warnings | 0 |  |  | # of Warnings | 0 |  |  | # of Warnings | 0 |  |  | # of Warnings | 0 |  |  | # of Warnings | 0
|  |  | Complexity Alert | None |  |  | Complexity Alert | None |  |  | Complexity Alert | None |  |  | Complexity Alert | None |  |  | Complexity Alert | None |  |  | Complexity Alert | None |  |  | Complexity Alert | None
Group | Parameter | Description | Answer | Score | Result | Comments | Answer | Score | Result | Comments | Answer | Score | Result | Comments | Answer | Score | Result | Comments | Answer | Score | Result | Comments | Answer | Score | Result | Comments | Answer | Score | Result | Comments
Process Details | # of Applications | How many applications are utilized in this process? ex. Excel, SAP, Bank Website, Jira Web App, Outlook…etc. Each unique website counts as 1 Application | 4-5 applications | 4 | Med | ACME System 1, ACME System 3, Exchange / Outlook, Excel, PDF
| Application Type(s) | Are any applications in scope are Mainframes or Terminals? | No | 0 | Low
| # of Screens | How many different screens/pages are utilized in this process, across all Applications? Ex. Login Screen counts as 1, loading the home page after login counts as 1 | 6-20 screens | 3 | Med
| # of Process Steps | How many steps are in the process, across all applications? A step can be also be defined as a small group of small steps. Ex. "3 Clicks to download a file" can be considered a step | 20-40 steps | 2 | Med
| # of Decisions | How many decision trees/forks are in the process, across all applications? Potential IF Statements or branches. Ex. "If value is <X do Y, if value >X, do Z" counts as 1 decision | 3-9 Decisions (If Branches) | 3 | Med
Data Input | Data Structure* | Is there unstructured digital inputs? Will the data location change with each case? Ex. from native PDFs, Word docs, Emails Body, etc… | No | 0 | Low
| # of Input Formats | How many different input formats are required to initiate the process? Ex. PDF Layout, Excel Sheet, Email, Web Data Table, etc… | 2 Inputs | 2 | Low
| OCR/Image Based Automation | Will OCR or IR be required to perform this process? Does process require data extraction from images and/or scanned PDFs? | Yes (Will Need OCR) | 5 | High | Input scanned PDF documents.
Misc | Strict SLA Rules | Are there Service Level Agreement (SLA) and Recovery Time Objective (RTO) that could potentially be impacted by the Automation Run time? | Some SLA Rules | 5 | Med
| PHI & Sensitive Data | Does the process contain PHI & Sensitive data that need to be stripped from documentations or kept from Developer? | No PHI or Sensitive Data | 0 | Low
| API Usage | How many API calls are in the process? Will it be required? API calls take longer and require more expertise to develop | No (API Access not needed/possible) | 0 | Low

## Reference Timeline & Effort
Low Complexity | High Level Time and Effort Estimates
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Planning and Setup
Business Case and Tech Validation
Gather Requirements
Solution Design
Development
System Testing
UAT
Deploy
Hypercare
Close
Role | [9 empty] | Total Hrs.
Project Manager | 16 | 2 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 44
Business Analyst | 4 | 20 | 4 | 4 | 4 | 2 |  |  | 6 | 44
Developer | 4 | 20 | 40 | 40 | 40 | 20 | 4 | 8 | 4 | 180
Solution Architect | 4 | 20 | 4 | 4 | 4 | 2 | 4 | 4 | 2 | 48
Engagement Manager | 8 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 22
338
Medium Complexity | High Level Time and Effort Estimates
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Planning and Setup
Business Case and Tech Validation
Gather Requirements
Solution Design
Development
System Testing
UAT
Deploy
Hypercare
Close
Role | [11 empty] | Total Hrs.
Project Manager | 16 | 2 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 52
Business Analyst | 4 | 40 | 4 | 4 | 4 | 4 | 2 | 2 |  |  | 6 | 70
Developer | 4 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 4 | 16 | 4 | 268
Solution Architect | 4 | 4 | 40 | 4 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 76
Engagement Manager | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 26
492
High Complexity | High Level Time and Effort Estimates
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Planning and Setup
Business Case and Tech Validation
Gather Requirements
Solution Design
Development
System Testing
UAT
Deploy
Hypercare
Close
Role | [16 empty] | Total Hrs.
Project Manager | 16 | 2 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 72
Business Analyst | 4 | 40 | 40 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 |  |  |  | 6 | 122
Developer | 4 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 4 | 16 | 16 | 4 | 444
Solution Architect | 4 | 20 | 40 | 40 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | [5 empty] | 130
Engagement Manager | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 36
804

## Estimates - Deliverable 1
Project Name | Vendor Onboarding
Customer Name
High Level Time and Effort Estimates
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Planning and Setup
Business Case and Tech Validation
Gather Requirements
Solution Design
Development
System Testing
UAT
Deploy
Hypercare
Close
Role
Project Manager
Business Analyst
Developer
Solution Architect
Engagement Manager

## Process Steps - Deliverable 2
Process Name | Vendor Onboarding
Process Summary | Extract details from the vendor onboarding form and insert vendor details in ERP Application. The MIS is prepared and shared with the business team.
End goal | Automated onboarding of 80% of new vendors.
Frequency | Daily
AHT (Average Handling Time) | 20 minutes manually / 4 minutes with RPA
Volume per year | 82125
Process Steps | Description | Application | Risks (if any)
1 | Retrieve the input emails. | Office 365 / Outlook | Access not provided to sample emails could delay the development.
2 | Login to ACME System 1. | ACME System 1 | Access not provided / permissions not set correctly could delay the development.
3 | Login to ACME System 3. | ACME System 3 | Access not provided / permissions not set correctly could delay the development.
4 | Retrieve the details from the input files. | Excel / PDF | Higher volumes of out of scope documents than expected would impact the Business Rule Exception volume.
5 | Search the vendor in ACME System 3. | ACME System 3
6 | Update vendor details to ACME System 1. | ACME System 1
7 | Send completion report. | Office 365 / Outlook
8
9
10
11
Key Assumptions:
1. UiPath Access to all systems, VMs, UiPath Studio, Orchestrator, Office on week 0 (before UiPath work starts)
3. Estimates of requirements is based on similar projects from the past. Estimates may need to be recalibrated once the PDD is signed off.
4. All electronic input, no Citrix or RDP automation required, no custom machine learning models, standard logging and output file
5. Infrastructure setup estimates are not included (UiPath to provide documentation for setup, customer executes)

## Parameter List & Scores (hidden)
Group | Parameters | Max Weight | Options | Mean Score | L/M/H? | Design Score | Dev Score | UAT Score | HyperCare Score | Parameter Description/Justifications | Warning Description | Group Weight
Process Details | # of Applications | 10 | Unknown (# of Applications) | 0 |  | 0 | 0 | 0 | 0 | An application can be: Excel, SAP, Outlook, Mainframe Note that "Browser" does not count as 1 application. Rather, each individual website will be counted as 1 Application. | N/A | 45
|  |  | 1 application | 1 | Low | [5 empty] | N/A
|  |  | 2-3 applications | 2 | Low | 2 | 2 | 2 | 2 |  | N/A
|  |  | 4-5 applications | 4 | Med | 4 | 4 | 4 | 4 |  | N/A
|  |  | 6-7 applications | 6 | High | 6 | 6 | 6 | 6 |  | N/A
|  |  | 8-9 applications | 8 | High | 8 | 8 | 8 | 8 |  | N/A
|  |  | >= 10 applications | 10 | High | 10 | 10 | 10 | 10 |  | N/A
| Application Type(s) | 5 | Unknown (Application Type(s)) | 0 |  | 0 | 0 | 0 | 0 | Each application type represents a different challenge for Automation due to user interface, coding language, and access differences. Microsoft applications are easier to automate due to compabitility with UiPath language, whereas a mainframe is more difficult since the automation will be most lkely be performed using a series of keystrokes | N/A
|  |  | No | 0 | Low | 3 | 3 | 3 | 3 |  | N/A
|  |  | Yes (Mainframe/Terminal) | 5 | High | 4 | 4 | 4 | 4 |  | N/A
| # of Screens | 10 | Unknown (# of Screens) | 0 |  | 0 | 0 | 0 | 0 | A sreen references how many different individual pages will be loaded. For example, going to a bank website to pull a transaction summary report will contain 3 screens: Login Screen, Home/Landing Page, and the Transaction summary screen. | N/A
|  |  | 0-5 screens | 0 | Low | 0 | 0 | 0 | 0 |  | N/A
|  |  | 6-20 screens | 3 | Med | [5 empty] | N/A
|  |  | 21-40 screens | 6 | High | 2 | 2 | 2 | 2 |  | N/A
|  |  | 41+ screens | 10 | High | 4 | 4 | 4 | 4 |  | N/A
| # of Process Steps | 10 | Unknown (# of Process Steps) | 0 |  | 0 | 0 | 0 | 0 | A process step can be defined as an action towards a objective. For example, "Download File" can be considered 1 step, but would require several clicks such as "Click Download, Select Destination, Name File, Click Save" Another example: "Log In" is 1 step, but involves "Enter user id, enter password, click login" | N/A
|  |  | 1-5 steps | 0 | Low | 0 | 0 | 0 | 0 |  | N/A
|  |  | 6-20 steps | 1 | Low | 2 | 2 | 2 | 2 |  | N/A
|  |  | 20-40 steps | 2 | Med | 4 | 4 | 4 | 4 |  | N/A
|  |  | 40-60 steps | 4 | Med | 6 | 6 | 6 | 6 |  | N/A
|  |  | 60-80 steps | 6 | High | [5 empty] | N/A
|  |  | 80-100 steps | 8 | High | [5 empty] | N/A
|  |  | 100+ Steps | 10 | High | 8 | 8 | 8 | 8 |  | N/A
| # of Decisions | 10 | Unknown (# of Decisions) | 0 |  | 1 | 1 | 1 | 1 | A decision is the equivalent of an "IF Statement". Each time the user/automation would need to evaluate which direction to go based on a set of rules, it is considered 1 decision. For ex: If the date on invoice is older than 3months, set status as "Archive". If date is within the last 3months, set status as "Valid". The more decisions in a process, the more testing that needs to be done to ensure the automation can effectily handle every decision branch | N/A
|  |  | 1-3 Decisions (If Branches) | 1 | Low | 1 | 1 | 1 | 1 |  | N/A
|  |  | 3-9 Decisions (If Branches) | 3 | Med | 3 | 3 | 3 | 3 |  | N/A
|  |  | 9-30 Decisions (If Branches) | 6 | High | 6 | 6 | 6 | 6 |  | N/A
|  |  | 30-70 Decisions (If Branches) | 10 | High | 10 | 10 | 10 | 10 |  | N/A
Data Input | # of Input Formats | 5 | Unknown (# of Input Formats) | 0 | [5 empty] | The number of different uniquely formatted inputs required to initiate a process. These inputs contain necesarry data to perform the process. For example, a process may require data from a contact directory table, An excel Parts List and an incoming email PDF attachment in order to begin the work. That will be considered as 3 uniquely formatted inputs. Note that if you have the same format input, such as 100 invoices with the same information but different vendors, it will count as 1 type of Input Format. However, if you have 2 PDF's with different formats, like 2 invoices types, it will count as 2 inputs formats. | N/A | 20
|  |  | 1 Input | 1 | Low | 0 | 0 | 0 | 0 |  | N/A
|  |  | 2 Inputs | 2 | Low
|  |  | 3 Inputs | 3 | Med
|  |  | 4 Inputs | 4 | Med | 2 | 2 | 2 | 2 |  | N/A
|  |  | >=5 Inputs | 5 | High | [5 empty] | N/A
| Data Structure | 10 | Unknown (Data Structure) | 0 |  | 0 | 0 | 0 | 0 |  | N/A
|  |  | No | 0 | Low | [5 empty] | N/A
|  |  | Yes (Unstructured/Free Text) | 10 | High | Warning | Warning | Warning | Warning |  | Free text fields or unstructured emails need to be analyzed to see any possibility of standardization. If rules cannot be clearly defined unattended automation might not be an option
| OCR Based Automation | 5 | Unknown (OCR Based Automation) | 0 |  | 5 | 5 | 5 | 5 | OCR is used when there are certain fields in a process that cannot be selected or recognized by convential RPA selectors. Examples include some fields in a Mainframe, Texts in an Image, unique applications that don't interact well with RPA, etc... | N/A
|  |  | Yes (Will Need OCR) | 5 | High | [5 empty] | N/A
|  |  | No (Will Not Need OCR) | 0 | Low | 0 | 0 | 0 | 0 |  | N/A
| Strict SLA Rules | 5 | Unknown (Strict SLA Rules) | 0 |  | 0 | 0 | 0 | 0 | A business process with strict SLA rules may require extra attention during development and testing to ensure the automation executes on a timely manner as to not violate SLA expectations | N/A
|  |  | No SLA Rules | 0 | Low | [5 empty] | N/A
|  |  | Some SLA Rules | 5 | Med
|  |  | Strict SLA Rules | 5 | High | 0 | 2 | 2 | 2 |  | N/A
| PHI & Sensitive Data | 5 | Unknown (PHI & Sensitive Data) | 0 |  | 0 | 0 | 0 | 0 | PHI and Sensitive data will affect the time consumption of documentation, and may result in additional measures of security during Development and Testing | N/A
|  |  | No PHI or Sensitive Data | 0 | Low | [5 empty] | N/A
|  |  | Some PHI & Sensitive Data | 5 | Med | 1 | 1 | 1 | 1 |  | N/A
|  |  | Mostly PHI & Sensitive Data | 5 | High | 3 | 3 | 3 | 3 |  | N/A
Environment Details | API Usage | 10 | Unknown (API Usage) | 0 |  | 0 | 0 | 0 | 0 | API usage is generally more stable than surface automation, but requires a more advanced developer to code the API service calls | N/A | 10
|  |  | No (API Access not needed/possible) | 0 | Low | [5 empty] | N/A
|  |  | 1-2 API Calls | 2 | Low
|  |  | 3-5 API Calls | 4 | Med
|  |  | 6-10 API Calls | 6 | Med
|  |  | 11-20 API Calls | 8 | High
|  |  | 20+ API Calls | 10 | High | 3 | 3 | 3 | 3 |  | N/A
[11 empty] | Total Score | 85
Complexity | Max Score
Low | 20
Medium | 35
High | 60
Very High | 100