## Test Plan
Technical Testing Plan
1 Introduction
1.1 Purpose of Document
This document is intended to outline testing as a criteria for completing Development & Testing and entering User Acceptance Testing
This document will clearly identify what the test deliverables will be and the timelines for these.
1.2 Test Execution Team
The names must be included in the table below.
Role | Responsibilties | Name | Contact details
(email address)
Executor | Build the test cases in code. Work with the Approver to | Joe Bratt (Developer) | Joe.bratt@mail.com
Approver | Review Test Results and provide approval. Sign-off on Completion | Charlie Pierce (Solution Architect/Tech lead) | Charlie.pierce@mail.com
2. Testing Types
2.1 Intro
This section is intended to outline many possible testing areas that a solution might need to encounter. This is dependent on requirements, so not all testing types need to be covered.
2.2 Functional Testing
Type | Description
Unit | Involves testing individual workflows in isolation, rather than testing the entire solution as a whole. The purpose of unit testing is to verify that each workflow performs as expected, and to catch and isolate defects or bugs early in the development cycle.
Integration | Verifies the interactions and communication between different components of your automation. The purpose of integration testing is to identify any issues or defects that arise when multiple workflows are integrated together, and to ensure that the solution as a whole performs as expected.
System | Verifies the complete functionality and performance of an automation system as a whole. The purpose of system testing is to ensure that the automation system can access all applications and performs as expected in its intended environment.
User Acceptance | Verifies whether an automation meets the needs and requirements of its intended users. The purpose of UAT is to ensure that the solution is ready for release to the end-users or customers and meets their expectations. User Acceptance test cases should be executed by the development team before they are attempted by the subject matter experts.
3.2 Non-Functional Testing
Parameter | Description
Performance | Evaluates the performance and responsiveness of an automation under various load conditions. The purpose of performance testing is to ensure that the automation can handle a specific level of workload/user traffic/etc., and to identify any performance-related issues or bottlenecks.
Usability | Asseses the ease of use and user experience of an automation. The purpose of usability testing is to ensure that the automation is easy to use and understand for its intended audience, and to identify any usability issues or problems that may affect user adoption and satisfaction. This becomes critical for attended automations with large user bases.
Compatibility | Verifies whether a solution is compatible with various hardware, operating system, and software configurations. The purpose of compatibility testing is to ensure that the automation can run and operate seamlessly across different platforms and configurations, and to identify any compatibility-related issues or problems. For unattended automations, this is less important given the environment is pre-determined and can be enforced. This becomes critical for attended automations with large user bases.
6 Test Environment
Details for hour testing will occur during the development phase (should mirror UAT)
System/Application | Version | Thin/Thick | Time Availability | User Name
ACME | Web Application | Thin | 7 am - 20 pm EST
ACME System 3 | 6.2.9200.0 | Thick | 7 am - 20 pm EST
Outlook | Any | Thick | 0 am - 24 pm EST

## Technical Testing
Process Name | Vendor Onboarding |  |  | Pass | 0 | 0%
Technical Lead | Charlie Pierce |  |  | Fail (Low Sev.) | 0 | 0%
Developer | Joe Bratt |  |  | Fail (Med/High Sev.) | 0 | 0%
Robot Name | svc-botp-venonb-001 |  |  | Not Run | 21 | 100%
Machine Name | Dcuiprpasvpd01 |  |  | Total | 21 | 100%
# | Case | Additional Testing Details | Case ID | Type | Status | Fail Severity | Expected Result / screenshots | Actual Result / screenshots | Defect ID | Fail Reason/Next Action | Screenshots | Author | Create Date | Executor | Run Date | Approver | Approval Date
1 | Read Inbox | Read the inbox | VONB001 | 1. Unit | Not Run | N/A | The bot should be able to read the inbox
2 | The bot is unable to access the inbox |  | VONB002 | 1. Unit | Not Run | N/A | The robot should terminate and log a business exception
3 | Download Attachment | Download attachement (pdf, xlsx) from the email that contains the subject "New Vendor received" | VONB003 | 2. Integration | Not Run | N/A | The robot should save the attachement in the Input Folder
4 | Attachment not found | The email does not contain any attachment | VONB004 | 2. Integration | Not Run | N/A | If attachment not found, notify Vendor
5 | Multiple attachements found | The email contain multuple attachments | VONB005 | 2. Integration | Not Run | N/A | If more than oneattachment found, notify Vendor
6 | Invalid file type | The email contains attachment different than xlsx or pdf | VONB006 | 2. Integration | Not Run | N/A | If Invalid FileType found, notifyVendor
7 | Vendor details missing | Vendor details are missing from the downloaded file | VONB007 | 2. Integration | Not Run | N/A | If vendor details missing, notifyvendor
8 | TaxId not valid | Tax ID is not valid, | VONB008 | 1. Unit | Not Run | N/A | If Tax ID is not valid, notify vendor.
9 | Login to the ACME Application | Log in using correct credentials (username and password) | VONB009 | 2. Integration | Not Run | N/A | The Bot should be able to login to the ACME
10 | The Bot is unable to log into ACME Application | Log in using incorrect credentials (username and password) | VONB010 | 2. Integration | Not Run | N/A | Retry 3 times else the Bot should terminate and log a business exception and notify support team
11 | ACME Webpage does not repond | The robot cannot access ACME webpage | VONB011 | 1. Unit | Not Run | N/A | Restart 3 times the browser, else the Bot should terminate and log a business exception and notify support team
12 | The robot can search for a vendor | 1. Click on the ‘Home’ button 2. From the Vendors tab, select Search for Vendor option from the drop-down menu. 3. Enter the Tax IDin the Vendor TaxID section andselect the Searchbutton | VONB012 | 3. System | Not Run | N/A
13 | Vendor found | Vendor is found | VONB013 | 3. System | Not Run | N/A | If vendor ispresent indatabase, notify vendor
14 | The robot can log in in AMCE System 3 | Log in using correct credentials (username and password) | VONB014 | 2. Integration | Not Run | N/A | Login to ACME System 3
15 | The robot cannot log in AMCE System 3 | Log in using incorrect credentials (username and password) | VONB015 | 2. Integration | Not Run | N/A | Retry 3 times else the Bot should terminate and log a business exception and notify support team
16 | The robot can search for a Tax ID | Search for the Tax ID in Client Data. | VONB016 | 3. System | Not Run | N/A | If a vendor is present indatabase, notify Vendor
17 | The robot saves Vendor in ACME | 1. If not vendor is found, Navigate to Vendors>Add Vendor in ACME. 2. Click on Add Vendor Page 3. Enter Vendor Tax ID, Vendor Name, Address, City and Country extracted from the mail attachment. | VONB017 | 3. System | Not Run | N/A
18 | The robot cannot save robot in ACME |  | VONB018 | 3. System | Not Run | N/A | The robot will throw an exception
19 | The robot creates the MSI report |  | VONB019 | 4. User Acceptance | Not Run | N/A | Update MIS Report
20 | The robot does not create MSI report |  | VONB020 | 1. Unit | Not Run | N/A | The robot will throw an exception
21 | The robot will send the MSI report to the concerned department. |  | VONB021 | 4. User Acceptance | Not Run | N/A | Send mail to business team with MIS Report as Mail Attachment

## Lists (hidden)
Types
1. Unit
2. Integration
3. System
4. User Acceptance