## Instructions
How to use UAT Test Plan?
Step | Instructions | Note
1 | Rename this file with the company and process name | Change process names inside "UAT Test Cases" sheet as well
2 | Fill the "UAT Test Cases" sheet along with the PDD. | All the scenarios that will be developed and tested should be documented in the UAT Test Cases sheet
3 | Get approval on the UAT Test Cases | This can be done along with the PDD or once PDD is signed off
4 | The "Test Plan" should be filled out before the start of the UAT | Examples are provided to denote the type of data that can be put in in the various sections and these are marked in grey font. Replace these with process specific data. This sheet should be filled by the BA along with the SA and developers.
5 | Communicate the "Test Plan" to the stakeholders | Sign-off ón Test Plan can be obtained at this stage
6 | Enter the run results in "UAT Test Cases" sheet | During UAT, make copies of the "UAT Test Cases" sheet everyday and fill the run results. This will be handed over to the client when requesting UAT Sign-off. The issues/bug/changes identified on a daily basis will be updated in this sheet
7 | Update "Issue Tracker" to consolidate the list of issues faced in UAT | This sheet can be used to have a consolidated list of issues/bug/changes that were reported during UAT. This will be the exhaustive list of items that were reported during the entire course of UAT.

## UAT Test Cases
Process Name | Vendor Onboarding |  |  |  | Pass | 0 | 0%
Process Owner | XYZ |  |  |  | Fail (Low Sev.) | 0 | 0%
Robot Name | svc-botp-venonb-001 |  |  |  | Fail (Med/High Sev.) | 0 | 0%
Machine Name | Dcuiprpasvpd01 |  |  |  | Not Run | 4 | 100%
[5 empty] | Total | 4 | 100%
# | Requirement | Additional Testing Details | Case ID | Test Category | Type | Status | Fail Severity | Expected Result / screenshots | Actual Result / screenshots | Defect ID | Fail Reason/Next Action | Screenshots | Author | Create Date | Executor | Run Date | Approver | Approval Date
1 | Login to the CRM Application | 1. Log in using correct credentials (username and password) | VONB001 | Business | Positive | Not Run | N/A | The Bot should be able to login to the Gmail Account
2 | The Bot is unable to log into CRM Application | 1. Log in using incorrect credentials (username and password) | VONB002 | Business | Negative | Not Run | N/A | Retry 3 times else the Bot should terminate and log a business exception
3 | Download attachment from email | 1. Email contains 1 attachement 2. Attachement type= .pdf | VONB003 | Business | Positive | Not Run | N/A | Bot is able to download attachement
4 | Multiple attachemnts added to email | 1. Email contains 3 attachements 2. Attachements type= .pdf | VON004 | Business | Positive | Not Run | N/A | The Bot terminates and sends an email to the vendor mentioning that "multiple attachements added to email"
5 | Unable to download attachment from email | 1. email has no attachement | VON005 | Business | Negative | Not Run | N/A | The Bot terminates and sends an email to the vendor mentioning that "no attachement found"

## Test Plan
Test Plan Document
1 Introduction
1.1 Purpose of Document
The Test Plan has been created to communicate the test approach to team members, what is deemed in and out of scope for testing
It includes the objectives, scope, schedule, risks and key milestones. This document will clearly identify what the test deliverables will be and the timelines for these.
1.2 Test Execution Team
The names must be included in the table below (examples are provided in grey, replace it with process specific data)
Role | Responsibilities | Name | Contact details
(email address)
Executor/SME | Provide test data before the start of UAT. Run the test cases and validate the results. Work with the development team to ensure that issues are properly triaged and resolved | abc | abc@xyz.com
Approver | Review Test Results and provide approval. Sign-off on UAT Completion | bcd | bcd@xyz.com
1.3 Test Support Team
The names must be included in the table below (examples are provided in grey, replace it with process specific data)
Role | Responsibilities | Name | Contact details
(email address)
Business Analyst | Create UAT Test Plan and develop test cases. Ensure execution of test cases and validate results. Identify any scope creep and maintain issue tracker . | BBCC | bbcc@uipath.com
Developer | Implement any changes required to the solution and test it before deploying. Provide support to the testing team by answering questions, addressing issues, and providing guidance on how to use the RPA solution. | TBD | TBD
Project Manager | Responsible for managing the overall project and ensuring that the testing is executed within the set timelines and budgets. | xxyy | xxyy@uipath.com
Infra/IT Team | Set up the Test Environment of applications and systems required for Testing | TBD | TBD
2.1 In Scope for Testing
The activities IN scope for Testing are listed here:
1 | Retrieving email attachements
2 | Search for Tax ID in the mail attachements
3 | Extracting data from the documents
4 | ACME System 1 navigation and login
5 | ACME System 3 navigation and login
6 | Data entry into ACME System 1
8 | Emailing/Notifying Vendor team of successful onboaring or any errors or exceptions
2.2 Out of Scope for Testing
The activities OUT of scope for Testing, are listed here.
1 | Troubleshooting errors
3 Acceptance Criteria
3.1 Functional Criteria
Parameter | Description
Functionality | Bot extracts details from the vendor onboarding form and insert vendor details in ERP Application All business and system exceptions are handled as per PDD and SDD
Accuracy | The usernames/alias are accurately created
Completeness | All the in-scope requirements mentioned in the PDD and UAT test cases will be executed by the bot
Compatability | The BOT is able to integrate with other systems, perform data transfers, and interact with the required interfaces via API
3.2 Non-Functional Criteria
Parameter | Description
Scalability | 1. The solution can be easily scaled up to handle more runs per day, without requiring significant modifications to the system architecture or infrastructure.
Reliability | 1. Unknown exceptions such as pop up windows, connection timeouts or database connection failures are handled in the code 2. Bots can maintain system logs and audit trails of all system interactions and activities, including any errors or exceptions, for at least 90 days.
Efficiency | 1. Bots can process the daily volume within the predefined SLA
Change Management | 1. Any process, input step or requirement not document in the PDD will have to go through a change management process
Security and Data Management | 1. Credentials are stored securely in Orchestrator (Assets) 2. Bot access the applications in scope as per expectations and has the required roles only for performing the process.
Compliance | 1. Bots can provide real-time alerts and notifications to system administrators in the event of any security breaches or unauthorized access attempts. 2. Bots can meet all relevant security standards and regulations, such as GDPR, HIPAA, and PII
Usability | N/A (there is no user interface in scope for this process)
Performance | BOT has been tested for response time and processing large volume of data
4 Assumptions
Category | Description | Owner | Due Date | Status | Actions/Comment’s
Business Team | Business team will be available to validate the run result and provide feedback on a daily basis during the UAT phase | Project Owner | XX-XX-XXXX
Data | Testing will be done based on the work items available in the queue. If any scenario is not covered during the UAT, further testing could cover all scenarios as per requirement and increase the UAT timelines | Test team | XX-XX-XXXX
Application | Dev and test environment would be same and in case of any deviations additional development might be required | Test team | XX-XX-XXXX
5 Risks
Type | Description | Impact | Trigger | Mitigation Plan
Business Team | SME unavailability | Run result will not be validated and could delay go-live | none | Backup members to be made available during the UAT phase
Data Quality | Incomplete testing due to unavailability of all test cases | Untested scenarios might be deployed in prod | none | Test data should be prepared prior to UAT and should cover all test cases
Application | CRM/ERP or application unavailability | UAT could be extended and cause delay in timelines | System outage | Customer technical support to be readily available to quickly resolve any issues that may arise during UAT
Operational | Scope creep causing additional testing beyond what was planned | UAT could be extended and cause delay in timelines | Additional requirements | Change management should be followed to minimize scope creep
6 Test Environment
A dedicated testing environment with test server are needed for testing phase.
System/Application | Version | Thin/Thick | Time Availability | User Name
CRM |  | Thin | 9 am - 5 pm EST | TBD
ERP |  | Thin | 9 am - 5 pm EST | TBD
|  | Thin | 9 am - 5 pm EST | TBD
7 Test Approach
Methodology | Status (Y/N)
Agile
Waterfall
Agile and Waterfall
8 Test Data
The data that will be used during testing, including test data, production data, and any other relevant data. (examples are provided in grey, replace it with process specific data)
Data Type | Source | Format | Number of transactions/ documents required | TAT | Environment | Approval required
XYZ Report | CRM | Excel | 10 | 1 day | Prod | Yes
Vendor List | CRM | Excel | 50 | 1 day | Prod | Yes
KYC Documents | CRM | PDF | 50 | 2 days | Test | No
9 Milestones/ Deliverables
9.1 Test Schedule (modify as per requirement)
Testing timeline, including the duration of each test phase and the estimated time to complete each test. (examples are provided in grey, replace it with process specific data)
Task Name | Start | Finish | Effort/Hours Required | Status | Responsible | Actions/Comment’s
Test Planning | XX-XX-XXXX | XX-XX-XXXX | 2 hours | Complete | PM, Test Support Team
Review Requirements documents and Test case documents |  |  |  |  | Test Support Team
Test Script preparation |  |  |  |  | Test Support Team
Test script review and updates |  |  |  |  | Test Support Team
First deploy to QA |  |  |  |  | Developer and SA
Process flow testing (Test Script execution) |  |  |  |  | Developer and SA
Process and Objects code verification |  |  |  |  | Developer and SA
Load testing |  |  |  |  | Developer and SA
Defect-retesting, if any |  |  |  |  | Developer and SA
Regression testing |  |  |  |  | Developer and SA
Resolution of final defects and final build testing |  |  |  |  | Developer and SA
UAT execution |  |  |  |  | Test execution and test support team
UAT Sign-off |  |  |  |  | Approver
9.2 Deliverables
Deliverable | For | Date/Milestone
Test Plan | Project Manager; Test Support Team
Test Results | Test Lead, Project Manager
Test Summary report | Test Lead, Project Manager
10 Exit Criteria
Category | Criteria
Functional | 1. BOT is performing all the steps captured in SDD/PDD document (functional testing) 2. UAT runs are shared with users for validation on daily basis 3. BOT is successfully running against all the test scenario listed part of initial project requirement 4. Reported medium-high impacting issues are fixed by UiPath team
Application | 1. No unexpected change in application behaviour in UAT phase 2. All the in-scope applications have been tested against the positive and negative scenarios
Schedule | 1. BOT is scheduled in orchestrator for unattended run as per schedule time agreed between UiPath & Business team
Training | User demo on manual intervention/BOT trigger from orchestrator
Sign-off | UAT sign off from relevant stakeholders
Go-Live | 1. Go-live plan, including migration of data, cut-over procedures, and any other relevant steps, must be finalized and approved 2. A post-implementation review must be completed to assess the effectiveness of the automation process and identify any areas for improvement.

## Issue Tracker
S.No | Issue/Change | Issue Raised On | Analysis | Issue Type | Action Owner | Status | ETA | Comments
1 | Slowness of VM causing performance issues during BOT runs. | 2022-08-05 | RAM usage was high during BOT runs. | TS setup not adequate | Client | Closed |  | RAM increased to 32 GB by client on 08/12.